## FUNDRAISING
CENTORA ERP DEFECT TRACKER
Defect ID | TESTCASE ID | SUB MODULE | TITLE | SUMMARY/ DESCRIPTION | SEVERITY | PRIORITY | STEPS TO REPRODUCE | EXPECTED RESULT | ACTUAL RESULT | STATUS | STATUS | SCREENSHOTS | COMMENTS | DEVELOPER ASSIGNED | DATE RAISED | DATE RESOLVED
DF-01 | FUR_015 | Proposal Management | Proposal Creation | Users are unable to create proposal using AI wizard | critical | High | 1. Upon successful login, 2 Click on proposal management button 3. Click on create proposal button 4. A modal will be visible 5. Input all the text fiellds (proposal title,select opportunity, creation method,) 6. Click on create proposal 7. Select creation method- use AI wizard | The user should be able to create proposal successfully using AI wizard | Not as expected | Completed | Completed | https://prnt.sc/bRSgAWXo02Fw | Ready for retest | Abubakar Abdulrazaq | 22/09/2025 | 2025-10-02
DF-02 | FUR_016 | Proposal Management | Proposal Creation | Users are unable to create proposal using upload donor template | critical | High | 1. Upon successful login, 2 Click on proposal management button 3. Click on create proposal button 4. A modal will be visible 5. Input all the text fiellds (proposal title,select opportunity, creation method,) 6. Click on create proposal 7. Select creation method- upload donor template | The user should be able to create proposal successfully using upload donor template | Not as expected | Completed | Completed | https://prnt.sc/-uC7w63MSoQH | Ready for retest | Abubakar Abdulrazaq | 22/09/2025
DF-03 | FUR_017 | Proposal Management | Proposal Creation | Users are unable to create proposal using reuse proposal from library | Major | High | 1. Upon successful login, 2 Click on proposal management button 3. Click on create proposal button 4. A modal will be visible 5. Input all the text fiellds (proposal title,select opportunity, creation method,) 6. Click on create proposal 7. Select creation method- upload donor template | The user should be able to create proposal successfully using reuse proposal from library | Not as expected | Completed | Completed | https://prnt.sc/Oc1DAiCTz5x1 | Ready for retest | Abubakar Abdulrazaq | 22/09/2025
DF-04 | FUR_018 | Proposal Management | Proposal Creation | Users are unable to create proposal using create manually | Major | High | 1. Upon successful login, 2 Click on proposal management button 3. Click on create proposal button 4. A modal will be visible 5. Input all the text fiellds (proposal title,select opportunity, creation method,) 6. Click on create proposal 7. Select creation method- upload donor template | The user should be able to create proposal successfully manually | Not as expected | Not Started | Not Started | https://prnt.sc/TpZldEXZ4Bho | Upon submitting a single proposal, it automatically creates multiple times https://prnt.sc/fu38sr_3Tcp9 | Abubakar Abdulrazaq | 22/09/2025
DF-05 | FUR_019 | Proposal Management | Search Button | Search Proposal button is not functional | critical | Medium | 1. Upon successful login, 2 Click on proposal management button 3. Click on create proposal button 4. A modal will be visible 5. Input all the text fiellds (proposal title,select opportunity, creation method,) 6. Click on create proposal 7. Select creation method- upload donor template | Search proposal button should be functional | Not as expected | Not Started | Not Started | https://prnt.sc/5yfiloJK95g6 |  | Abubakar Abdulrazaq | 22/09/2025
DF-06 | FUR_020 | Proposal Management | Edit Button | Edit button is not functional | critical | medium | 1. Upon successful login, 2 Click on proposal management button 3. Click on search proposal button | user should be able to edit a proposal successfully | Not as expected | Not Started | Not Started | https://prnt.sc/sxulWbnNdNwg |  | Abubakar Abdulrazaq | 22/09/2025
DF-06 | FUR_021 | Proposal Management | Delete Button | Delete button is not functional | critical | medium | 1. Upon successful login, 2 Click on proposal management button 3. Click on search proposal button | user should be able to delete a proposal successfully | Not as expected | Not Started | Not Started | https://prnt.sc/sxulWbnNdNwg |  | Abubakar Abdulrazaq | 22/09/2025

## USER MANAGEMENT
CENTORA ERP DEFECT TRACKER
Defect ID | TESTCASE ID | SUB MODULE | TITLE | SUMMARY/ DESCRIPTION | SEVERITY | PRIORITY | STEPS TO REPRODUCE | EXPECTED RESULT | ACTUAL RESULT | STATUS | STATUS | SCREENSHOTS | COMMENTS | DEVELOPER ASSIGNED | DATE RAISED | DATE RESOLVED
DU-01 | USM_008 | USERS | Search user button is not working as expected | Search user button is not working as expected, upon entering the first letter, user has to click on space bar to be able to input subsequent letters | critical | High | 1. Launch the URL 2. Click on sign in button 3.Enter correct email address 4. Enter correct password 5. Click on login button 6. Upon successful login 7. Click on switch accout button 8. Click on user management 9. Click on the search button | Search button should be functional | Not as expected | Not Started | Completed | https://prnt.sc/258UuZlDE9rN |  | Abubakar Abdulrazaq | 23/09/2025
Completed
Completed
Not Started
Not Started
Not Started
Not Started

## DOCUMENT
CENTORA ERP DEFECT TRACKER
Defect ID | TESTCASE ID | SUB MODULE | TITLE | SUMMARY/ DESCRIPTION | SEVERITY | PRIORITY | STEPS TO REPRODUCE | EXPECTED RESULT | ACTUAL RESULT | STATUS | STATUS | SCREENSHOTS | COMMENTS | DEVELOPER ASSIGNED | DATE RAISED | DATE RESOLVED
DD-01 | DOC_007 | DOCUMENTS | Quick links- Upload document | Users are unable to upload document successsfully | critical | High | 1. Launch the URL 2. Click on sign in button 3.Enter correct email address 4. Enter correct password 5. Click on login button 6. Upon successful login 7. Click on switch accout button 8. Click on document manager 9.Click on quick links 10. Click on upload document | Upload button should be functional | Not as expected | Not Started | Completed | https://prnt.sc/DGQ5X7tFxP4r |  | Abubakar Abdulrazaq | 25/09/2025
DD-02 | DOC_011 | DOCUMENTS | Open setting button is not functional | When a user clicks on open setting button , the user is redirected to fundraising module | critical | High | 1. Launch the URL 2. Click on sign in button 3.Enter correct email address 4. Enter correct password 5. Click on login button 6. Upon successful login 7. Click on switch accout button 8. Click on document manager 9.Click on quick links 10. Click on open settings button | open setting button should be functional | Not as expected | Not Started | Completed | https://prnt.sc/lQf_5SGW9zFr |  | Abubakar Abdulrazaq | 25/09/2025
DD-03 | DOC_019 | DOCUMENTS | Document upload is not functional | Upload document button is not workong as expected | critical | High | 1. Launch the URL 2. Click on sign in button 3.Enter correct email address 4. Enter correct password 5. Click on login button 6. Upon successful login 7. Click on switch accout button 8. Click on document button 9. Click on upload button to upload a document 10 | Search button should be functional | Not as expected | Not Started | Completed | https://prnt.sc/5mHsGcFDIp6A |  | Abubakar Abdulrazaq | 23/09/2025
DD-04 | DOC_020 | DOCUMENTS | Edit document is not functional | Save draft and save changes button remains unclickabe | Major | Medium | "1. Launch the URL 2. Click on sign in button 3.Enter correct email address 4. Enter correct password 5. Click on login button 6. Upon successful login 7. Click on switch accout button 8. Click on document button 9. Click on the document to preview 10. Click on save draft 11.Click on save changes" | Edit document should be functional | Not as expected | Not Started | Not Started | https://prnt.sc/R2Hxf9qR87de |  | Abubakar Abdulrazaq | 25/09/2025
DD-05 | DOC_025 | E-SIGNATURE | Users are unable to request for signature by choosing from the library | Users ges error upon choosing a file from the library | Major | High | "1. Launch the URL 2. Click on sign in button 3.Enter correct email address 4. Enter correct password 5. Click on login button 6. Upon successful login 7. Click on switch accout button 8. Click on document button 9. Click on request for E-signature button 10. Choose a document from the library " | Request from library should be functonal | Not as expected | Not Started | Not Started | https://prnt.sc/-j3F3J3TJ_0I |  | Abubakar Abdulrazaq | 25/09/2025
DD-06 | DOC_029 | E-SIGNATURE | Close button is not clickable | user gets stuck at the point of closing modal upon viewing details | Major | High | "1. Launch the URL 2. Click on sign in button 3.Enter correct email address 4. Enter correct password 5. Click on login button 6. Upon successful login 7. Click on switch accout button 8. Click on document button 9. Click on request for E-signature button 10. Click on view 11. Click on close button to close the modal" | Request from library should be functonal | Not as expected | Not Started | Not Started | https://prnt.sc/HvniWDN-O6Bi |  | Abubakar Abdulrazaq | 25/09/2025
DD-07 | DOC_032 | Signature tracking | All department filter button is not functional | Upon clicking it returns same response for different filtering | Major | High | "1. Launch the URL 2. Click on sign in button 3.Enter correct email address 4. Enter correct password 5. Click on login button 6. Upon successful login 7. Click on switch accout button 8. Click on document button 9. Click on request for E-signature button " | FIlter button should be functional | Not as expected | Not Started | Not Started | https://prnt.sc/6xAVpLx5R0fF |  | Abubakar Abdulrazaq | 25/09/2025
DD-08 | DOC_038 | Signature tracking | Search button is not functional | upon clicking certificate of completion, search button iis functional | Major | High | "1. Launch the URL 2. Click on sign in button 3.Enter correct email address 4. Enter correct password 5. Click on login button 6. Upon successful login 7. Click on switch accout button 8. Click on document button 9. Click on request for E-signature button 10. Click on certificate of completion 11. Click on search document | Search button should be functional and responsive | Not as expected | Not Started |  | https://prnt.sc/5fvN9B36lGrb |  | Abubakar Abdulrazaq | 25/09/2025
DD-09 | DOC_039 | Signature tracking | All department filter button is not functional | Upon clicking it returns same response for different filtering | Major | High | "1. Launch the URL 2. Click on sign in button 3.Enter correct email address 4. Enter correct password 5. Click on login button 6. Upon successful login 7. Click on switch accout button 8. Click on document button 9. Click on request for E-signature button 10. Click on signed document history 11. Click on search document | Search button should be functional and responsive | Not as expected | Not Started |  | https://prnt.sc/5fvN9B36lGrb |  | Abubakar Abdulrazaq | 25/09/2025

## GRANT MANAGEMENT
CENTORA ERP DEFECT TRACKER
Defect ID | TESTCASE ID | SUB MODULE | TITLE | SUMMARY/ DESCRIPTION | SEVERITY | PRIORITY | STEPS TO REPRODUCE | EXPECTED RESULT | ACTUAL RESULT | STATUS | STATUS | SCREENSHOTS | COMMENTS | DEVELOPER ASSIGNED | DATE RAISED | DATE RESOLVED
DG-01 | GRT_007 | DASHBOARD | ERROR MESSAGE ON DASHBOARD | Upon switching to grant management module, error message pops up countless times | Critical | High | "1. Launch the URL 2. Click on sign in button 3.Enter correct email address 4. Enter correct password 5. Click on login button 6. Upon successful login 7. Click on switch accout button 8. Click on grant management" | Switching module to grant management should be seemless without error | Not as expected | Not Started | Completed | https://prnt.sc/vzfewxwfAqT- |  | Abubakar Abdulrazaq | 26/09/2025
DG-02 | GRT_009 | DASHBOARD | ERROR MESSAGE ON DASHBOARD | Upon switching to grant management module, error message pops up countless times | Critical | High | "1. Launch the URL 2. Click on sign in button 3.Enter correct email address 4. Enter correct password 5. Click on login button 6. Upon successful login 7. Click on switch accout button 8. Click on grant management" | Switching module to grant management should be seemless | Not as expected | Not Started | Completed | https://prnt.sc/vzfewxwfAqT- |  | Abubakar Abdulrazaq | 26/09/2025
DG-03 | GRT_010 | DASHBOARD | Filter button is not functional | Filter, edit and delete button is not functional | Critical | High | "1. Launch the URL 2. Click on sign in button 3.Enter correct email address 4. Enter correct password 5. Click on login button 6. Upon successful login 7. Click on switch accout button 8. Click on grant management 9. Click on filter button" | Filter button should be functional | Not as expected | Not Started | Completed | https://prnt.sc/vzfewxwfAqT- |  | Abubakar Abdulrazaq | 26/09/2025
DG-04 | GRT_009 | DASHBOARD | Edit and delete button is not functional | Filter, edit and delete button is not functional | Critical | High | "1. Launch the URL 2. Click on sign in button 3.Enter correct email address 4. Enter correct password 5. Click on login button 6. Upon successful login 7. Click on switch accout button 8. Click on grant management 9. Click on filter button" | Filter button should be functional | Not as expected | Not Started | Not Started | https://prnt.sc/vzfewxwfAqT- |  | Abubakar Abdulrazaq | 26/09/2025
DG-05 | GRT_018 | COMPLIANCE CHECKLIST | DASHBOARD | Filter, edit and delete button is not functional | Critical | High | 1. Launch the URL 2. Click on sign in button 3.Enter correct email address 4. Enter correct password 5. Click on login button 6. Upon successful login, click on add new donor 7. Click on switch accout button 8. Click on user account button 9. Click on search button 10. Click on filter button | Filter button should be functional | Not as expected | Not Started | Not Started | https://prnt.sc/vzfewxwfAqT- |  | Abubakar Abdulrazaq | 26/09/2025
| GRT_021 | DISBURSEMENT SCHEDULE | New Disbursement | Newly added disbursement is not visible on the top | Major | High | 1. Launch the URL 2. Click on sign in button 3.Enter correct email address 4. Enter correct password 5. Click on login button 6. Upon successful login, click on add new donor 7. Click on switch accout button 8. Click on user account button 9. Click on search button 10. Click on add new disbursement | Newly added disbursement should be visible on top of list | Not as expected | Not Started | Not Started | https://prnt.sc/8be036t-ZfQj |  | Abubakar Abdulrazaq | 26/09/2025
Not Started